## Project Plan
Tab 3.1 ¦ Leadership Position Outreach Plan
Note: This is an example of an outreach plan and timeline one might create to widely disseminate a leadership position opening. The process of outreach, however, will vary depending upon the position and the timing in which it needs to be filled.
# | Activity | Who | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 10
|  |  | Launch Open Call |  |  | Application Review |  | Interviews |  | Select Finalist | Selection Announced
1 | Complete job description to include required/desired qualification | Supervisor or person in role
2 | Align required/desired qualification with evaluation criteria | PM
3 | Determine interview questions | Supervisor + SLSC
4 | Email announcement to faculty, incl. role description + open call timeline | Chair
5 | Announce open call, job description, + timeline at faculty meeting and in departmental newsletter | Chair or Supervisor
6 | Informal networking, including encouraging women and URG faculty to apply | Supervisor, Chair + SLSC
7 | Reminders about open call and application deadline in all departmental meetings | Chair
8 | Email reminder of approaching application deadline date | Chair
9 | Application deadline
10 | Outreach to candidates not selected for interview * IF APPLICABLE, LIKELY NOT* | Supervisor
11 | Conduct candidate interviews | Chair, Supervisor, SLSC
12 | Outreach to candidate(s) not selected; should be in-person and clearly describe the ways in which an applicant did not meet the qualifications and include suggestions for training or experiential opportunities to better position them for being selected for higher level roles | Supervisor
13 | Announce new appointment @ faculty meeting and in newsletter as appropriate | Chair
14 | Written notification to Office of EVI/Megan + Kate of search result and diversity report | Chair